## SBRI action log
SBRI Healthcare Programme - meetings action log 2 October 2018
Project Name
Date | Meeting | Action | Person Responsible | Target Date | Completed Date | Remarks | status
2018-07-19 | Board | Discussion with each AHSN and final proposal on Governance Review to be circulated to all AHSNs | KL/RB/RP | 2018-10-16 |  | Board meeting 7 November - Agenda Item 2.1 | in progress
2018-07-19 | Board | Full data set from Annual Survery to be shared with all AHSNs | CW | 2018-10-16 |  | Board meeting 7 November - Agenda Item 2.3 | completed
2018-03-15 | Board | Draft a rolling programme of themes over the next 3-6 years for a balanced portfolio | KL |  |  | Board meeting 7 November - Agenda Item 2.2 | in progress
2018-03-15 | Board | communicate with NHS-E to talk about and plan a discussion where the board can share their knowledge and expertise on the programme | RP |  |  | FAR and Board members have contacted NHSE and further discussions are planned. | in progress
2018-07-19 | FAR | review pre-contracting due diligence process including RAG rating and related protocol for funding approval. | JT |  |  |  | in progress
2018-10-16 | FAR | Register of interests and conflict of interests policy document to be amended | JT |  |  |  | in progress
2018-07-19 | FAR | NHS England to advise if underspend can be retained in programme | AC | 2018-10-16 |  | Confirmed | completed
2018-10-16 | FAR | Grant Thornton or PEM to send the FARC a confirmation of the SBRI cash balance held by HEE on behalf of NHS England as at 31 March 2018 | MP |  |  |  | in progress
2018-05-14 | FAR | Appoint Board additional representatives on FAR | AK | 2018-06-10 |  | Invitiation to AHSN Board members to join FAR issued. | in progress
2017-09-26 | FAR | Set meeting with NHSE to discuss the retendering process | KL | 2017-11-30 |  | Discussions with NHS-E ongoing | in progress
2018-05-14 | FAR | NHSE to share the Internal Audit report letter | KS |  |  | awaiting update | in progress
2018-07-19 | Board | Send details of Treasury note on pre-approval to EH | KL |  |  |  | completed
2018-07-19 | Board | Agenda to be revised for future meetings so that Register of Interests features earlier | KL |  | 2018-10-02 |  | completed
2018-05-21 | Board | Revise business plan to reflect feedback at board | KL | 2018-07-19 |  | board considered business plan 14 May 2018 and final agreement to be signed off at board 19 July 2018 meeting. | completed
2018-03-15 | Board | Discuss NHS England allowing 450k (uncontracted SBRI 14) to be carried forward into next year. | KL | 2018-03-31 | 2018-03-31 | SBRI 14 Ph1 Q1 payment held by Papworth for contracting and payment in 2018/19 | completed
2017-10-10 | Board | Communication plan to be drafted. | KL / IH | 2018-03-15 | 2018-03-15 | Presented to board 15 March 2018 | completed
2017-10-10 | Board | Plan Mid November teleconference to discuss recommendations further | KL | 2017-11-15 | 2017-11-13 | Telecon Borad meeting held 13 Nov 2017 | completed
2018-07-19 | FAR | Management accounts to be amended to reflect quarterly reporting and variances against previous quarter | MP | 2018-10-16 | 2018-10-02 | Agreed new format with AC and presented to FAR on 16th October | completed
2018-07-19 | FAR | PEM to be asked to confirm if audit was carried out to agreed scope & detail nature of due diligence issues raised in report | MP | 2018-10-16 | 2018-10-02 | Requested from PEM | completed
2018-07-19 | FAR | Conflict of interest policy to cover whole process | JT | 2018-10-16 | 2018-10-02 | Presented to FAR on 16th October | completed
2018-05-14 | FAR | write to AHSNs and AHSN network regarding SBRI engagement in Innovation Exchanges | KL | 2018-06-14 |  | Discussion visits planned for August 2018 | completed
2018-05-14 | FAR | Update Phase 1 and 2 company contracts with new clause on funding not being guaranteed GDPR requirements & survey/data sharing commitments | AB/JT | 2018-05-31 | 2018-06-26 | seek legal advice on GDPR clause | completed
2018-05-14 | FAR | Update privacy policy and data protection procedures | AB/JT | 2018-05-25 | 2018-05-22 | Circulated to FAR after last meeting | completed
2018-05-14 | FAR | Circulate a list of SBRI processes and procedures to be prioritised for review this year | AB/JT | 2018-07-10 | 2018-05-18 | Circulated to FAR after last meeting | completed
2017-09-26 | FAR | Finalise Audit management Letter with recommendations included | MP | 2017-10-31 | 2017-10-31 | requested from PEM | completed
2017-09-26 | FAR | Obtain from PEM footnote on overspend | MP | 2017-10-31 | 2017-10-31 | requested from PEM | completed
2018-05-14 | FAR | Circulate scope of audit to FAR for comment | MP | 2018-06-10 | 2018-05-15 |  | completed
2017-09-26 | FAR | Add re-tendering process to risk register | KL | 2017-10-03 | 2017-09-28 | presented to board | completed
2017-09-26 | FAR | E-mail supplementary paper showing end of year cash-flow and proposed solutions. | MP | 2017-10-03 | 2017-09-28 | circulated to FAR | completed
2017-09-26 | FAR | circulate the updated Complaints and FOI requests paper | JT | 2017-10-03 | 2017-09-26 | circulated to FAR | completed
2017-09-26 | FAR | Register of Interests to be amended to remove EAHSN role for DC | JT | 2017-10-03 | 2017-10-03 | presented to Board | completed

## data verfier
Board | in progress
FAR | completed
Q Review | not started
Governance Review
Board/FAR